## Sheet1
North Claines Parish Council
Risk Register Review - Approved July 2024
Item | Risk | Probability |  |  | Impact |  |  | Action/Mitigation | Owner | November 2024 update
|  | Low | Med: | High | Low | Med: | High
3rd Parties
1 | Member of the public slips, trips or falls on Open Areas. |  | M |  |  | M |  | Review of conditions of Open Areas at regular intervals. Comprehensive Public Liability insurance. Prismian lighting report acted upon and progress reported to PC meeting | Clerk | No accidents reported
2 | Injury or death to members of the public on equipment in public play areas. | L |  |  |  |  | H | Act on RoSPA report. Clear signage that public use at their own risk. Completion of weekly checklist by councillor Comprehensive Public Liability insurance in place. | Recreation Group | No accidents reported. Councillors check weekly and report issues to Clerk. November Finance Committee signed off Brum repairs quote
3 | Injury or death to members of the public due to lack of maintenance of Open Spaces. | L |  |  |  |  | H | Action on RoSPA report. Clerk issues reports by the public quickly to Recreation Group Chair. Ensure Contractors undertake relevant maintenance activities. Completion of weekly checklist by councillor. Annual Tree Survey of trees near roads and houses | Recreation Group | No accidents reported.
4 | Injury or death to members of the public whilst assisting with PC activities and/or events. | L |  |  |  |  | H | Ensure adequate safety briefings in advance of event to members of the public by a relevant and knowledgeable person. Ensure members of the public have adequte PPE for their activities. Ensure adequate management control of members of the public. | Events Committee Chair | No accidents reported.
External
5 | Breach of personal and/or PC data. | L |  |  |  | M |  | Computers to have comprehensive anti-virus software. Automatic Back-up of all data to secure independent storage device. | Clerk | No breaches in 2023/4
6 | Loss of or damage to archived documents. | L |  |  | L |  |  | Secure, fireproof storage location. Digitised copies. | Clerk | No incidents
7 | Damage/Theft to PC owned equipment, facilities, property, etc. | L |  |  |  | M |  | Secure storage and locked premises Adequate insurance cover . | Clerk | No incidents
8 | On-line security. | L |  |  | L |  |  | Clerk uses secure VPN internet access. Councillors to use ".gov" email address wherever practicable. Councillors to use computer access with anti-virus. | Clerk. Councillors. Technical support provided by AI Media | No breaches in 2023/24
9 | Fraud | L |  |  | L |  |  | Use a secure, trusted bank account. Finance group to make regular and irregular checks of invoices and bank statements and income. Use trusted local companies wherever practicable. | Clerk Finance group. | No breaches in 2024/25 but new financial regulations adopted in May 2024 require dual authorisation prior to payment
10 | Theft of documents | L |  |  | L |  |  | Documents to be kept in secure storage. Digital storage | Clerk | No incidents
Internal
11 | Costs exceeding Budget | L |  |  | L |  |  | Ensure the budget is fit for purpose. Clerk to monitor budget against costs at the time of any major expense and advise the Finance group. Finance group to monitor budget against costs quarterly. | Finance group | Actuals v budget review on 15 November no actions needed
12 | Lack of Councillor numbers to adequately carry out PC functions. |  | M |  |  | M |  | Chair to continue to use Newsletter to encourage residents to assist. Identify any non-essential activities that can be reduced or deferred. | Chair | There remain a number of councillor vacancies but key functions and events continue
13 | Non-compliance with financial regulations, for example VAT return, financial statements, audit, register of gifts & hospitality | L |  |  | L |  |  | Ensure regular checks of Standing Orders, Regulations, Policies, etc by all. Membership of CALC & CPRE to provide advice | Clerk. | Thorough review by Finance Group in July and November
14 | Failure or inadequate works carried out by lengthsman |  | M |  |  | M |  | Works to be inspected by a knowledgeable person and complaints by members of the public are discussed at NCPC meetings Regular and/or sporadic checks by Councillors. | Councillor Liaison with Lengthsman | Councillor appointed to work closely with Lengthsman and reports back to NCPC meeting. Appointment of handyman delayed but readvertised
15 | Absence or loss of use of Clerk | L |  |  | L |  |  | Temporary Responsible Person available via CALC Responsible Person to be shared with another Parish Council. | Chair | Credentials will be additionally held in secure storage accessible only by Chair
16 | Inadequate insurance provisions. | L |  |  |  |  | H | Clerk and Finance group to collectively review scope of insurance cover required before renewal. | Chair, Finance Chair and Clerk | Axa Inspire Public & Employers Liability Insurance policy cover renewed on 1 June 2024; review in March 2024 to ensure all needs ae met.
17 | Failure of PC to adequately address issues for which it is responsible. | L |  |  |  |  | H | Ensure the PC is aware of responsibilities. Ensure the Councillors are aware of their general and individual responsibilites. Ensure adequate training for Councillors. | Chair and all councillors | PC engaged expert advice when appropriate eg Planning Expert
18 | Failure of Councillors to adequately understand their roles and responsibilities. | L |  |  |  | L |  | Ensure the Councillors are aware of their general and individual responsibilites. Ensure adequate training for Councillors. | Chair | New councillors attended traiining courses and updated advice influenced decision making
19 | Failure of PC to adequately safeguard Councillors from assault or injury or death whilst conducting PC business. | L |  |  |  |  | H | Adequate safeguards are identified with event risk assessments Ensure adequate insurance cover. | Chair
20 | Injury or death to clerk during their employment activities. Often a lone worker | L |  |  |  |  | H | Adequate safeguards to be identified and actioned. Ensure adequate safety measures are identified and in place by a relevant knowledgeable person. Ensure adequate insurance cover. | Chair | Axa Inspire Public & Employers Liability Insurance policy cover until May 2025 but Clerk is to check Lone Worker aspect of policy